## Sheet1
Timesheet |  |  | Time | Hour Invoiced
[5 empty] | Total Hours | 67
[5 empty] | Hours Charged | 55
[5 empty] | Rate | 35
[5 empty] | Total | 2345 | Invoiced | 1925
[5 empty] | To Invoice | 420
2017-11-20 | Initial Meeting | Meeting | 1 | 1
2017-11-30 | Setup openAstro + Linux | Development | 4 | 4
2017-12-07 | Meeting Veruska | Meeting | 1 | 1
2017-12-08 | Initial Development of Web Scraping | Development | 5 | 5
2017-12-08 | Documentation and emailing | Documentation | 1.5 | 1.5
2017-12-10 | Parse dataset CSV | Development | 1.5 | 1.5
2017-12-11 | Parse CSV testing and city implement | Development | 4.5 | 4.5
2017-12-18 | Running full tests, pickle and fix pDOB | Development | 6.5 | 6.5
2017-12-18 | Summarising and sending email of progress | Documentation | 0.5 | 0.5
2018-01-22 | Implement and refactor results | Development | 3.5 | 3.5
2018-01-23 | Review compatibility and questions | Documentation | 3 | 3
2018-01-24 | Review and implement ph1 Compat rules | Development | 2 | 2
2018-02-01 | Meeting Veruska | Meeting | 1 | 1
2018-03-04 | Refactor and structure to class based | development | 6 | 6
2018-03-05 | reimplement compatibility scores | Development | 3 | 3
2018-03-06 | Fixing comppatibility and angle calculation | Development | 5.5 | 5.5
2018-03-08 | Writing up current status - email | Documentation | 0.5 | 0.5
2018-03-08 | fixing identified bugs | Development | 1.5 | 1.5
2018-03-27 | Meeting in town | Meeting | 1 | 1
2018-03-27 | Bug Fixing from meeting |  | 2.5 | 2.5
2018-04-09 | Checking over hand results and fixing sextile range | Development | 2 | 0
2018-04-23 | Implement local requests module | Development | 2 | 0
2018-04-30 | Including localRequests module and fixing some issues | Development | 4.5 | 0
2018-05-13 | Implementing Vertex parameter + full document output | Development | 3.5 | 0
0
0
0